## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10 | Day 11 | Day 12 | Day 13 | Day 14
User Story #2 | 8 |  | Finish
gathering information about convert |  | salam | Finish | 8 | 4 | 3 | 5 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Background design |  | donia | Finish | 11 | 1 | 1 | 2 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
desgin interface |  | salam w donia | Finish | 14 | 2 | 0 | 3 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
implementation |  | donia w mariam | Finish | 20 | 0 | 0 | 0 | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
test |  | salam | Finish | 17 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 | 8
gathering information about menu |  | sara | Finish | 18 | 4 | 3 | 3 | 2 | 1 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0
design interface about menu |  | salma ahmed | Finish | 19 | 0 | 0 | 0 | 3 | 2 | 3 | 0 | 4 | 1 | 0 | 2 | 2 | 1 | 1
design interface about cost |  | donia | Finish | 9 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
implementation about list of drinks |  | awatef | Finish | 14 | 2 | 0 | 1 | 4 | 0 | 0 | 2 | 3 | 0 | 0 | 1 | 0 | 0 | 1
implementation about list of food |  | salma ibrahim&mariam | Finish | 14 | 2 | 0 | 3 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0
implementation about costs |  | mariam&awatef&salma ibrahim | Finish | 12 | 0 | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 3
test |  | salma ahmed&&donia | Finish | 20 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 1 | 2 | 0 | 1 | 2 | 3 | 5
Total |  |  |  | 176 | 16 | 11 | 19 | 20 | 18 | 14 | 17 | 10 | 5 | 4 | 6 | 5 | 5 | 10
Ideal |  |  |  | 176 | 163.4286 | 150.8571 | 138.2857 | 125.7143 | 113.1429 | 100.5714 | 88 | 75.4286 | 62.8571 | 50.2857 | 37.7143 | 25.1429 | 12.5714 | 0
Actual |  |  |  | 176 | 165 | 155 | 140 | 130 | 112 | 110 | 100 | 90 | 77 | 56 | 40 | 30 | 19 | 0