## Sheet1
Story Points | Status | Scrum master | End | start | Responsible | Task Name | #Sprint
5 | finish | donia | 14/3/2018 | 2018-01-03 | awatef && salma ahmed&& sara | calculator | NUM 1
| finish |  | 2018-10-03 | 2018-09-03 | awatef && salma ahmed | desgin interface
| finish |  | 2018-12-03 | 2018-10-03 | sara && awatef | implementation
| finish |  | 2018-12-03 | 2018-12-03 | awatef | test
8 | finish | salma ahmed | 28/3/2018 | 15/3/2018 | donia && mariam && salma ibrahim | convert | NUM 2
| finish |  | 14/3/2018 | 13/3/2018 | salma | gathering information about convert
| finish |  | 17/3/2018 | 16/3/2018 | salma ibrahim&& donia | desgin interface
| finish |  | 19/3/2018 | 17/3/2018 | donia && mariam | implementation
| finish |  | 20/3/2018 | 20/3/2018 | salma ibrahim | test
11 | not finish | Awatef ahmed | 19/4/2018 | 2018-08-04 | all team | Menu | NUM 3
| finish |  | 2018-09-04 | 2018-08-04 | sara | gathering information about menu
| started |  | 16/4/2018 | 2018-09-04 | salma ahmed | design interface about menu
| finish |  | 2018-11-04 | 2018-09-04 | donia | design interface about cost
| finish |  | 2018-12-04 | 2018-10-04 | awatef | implementation about list of drinks
| not started |  | 17/4/2018 | 14/4/2018 | salma ibrahim&mariam | implementation about list of food
| started |  | 15/4/2018 | 10/42018 | awatef&salma ibrahim&mariam | implementation about costs
| started |  | 19/4/2018 | 2018-09-04 | salma ahmed&&donia | test
24 | [6 empty] | Total Points