## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10 | Day 11 | Day 12 | Day 13 | Day 14
User Story #2 | 8
gathering information about convert |  | salam | Finish | 8 | 4 | 3 | 5 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Background design |  | donia | Finish | 11 | 1 | 1 | 2 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
desgin interface |  | salam w donia | Finish | 14 | 2 | 0 | 3 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
implementation |  | donia w mariam | Finish | 20 | 0 | 0 | 0 | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
test |  | salam | Finish | 17 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 70 | 8 | 5 | 11 | 9 | 6 | 5 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal burndown |  |  |  | 70 | 65 | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Actual burndown |  |  |  | 70 | 68 | 63 | 58 | 48 | 50 | 48 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0