## Sheet1
Status | Scrum master | End | Start | Responsible | Task Name | #Sprint
Finish | Donia | 2018-03-14 | 2018-03-01 | Awatef && Salma Ahmed && Sara | Calculator | NUM 1
Finish |  | 2018-03-05 | 2018-03-01 | Awatef && Salma Ahmed | desgin interface
Finish |  | 2018-03-10 | 2018-03-05 | Sara && Awatef | implementation
Finish |  | 2018-03-14 | 2018-03-10 | Awatef | test
Finish | Salma ahmed | 2018-03-28 | 2018-03-15 | Donia && Mariam && Salma Ibrahem | Convert | NUM 2
Finish |  | 2018-03-17 | 2018-03-15 | Salma Ahmed | Gathering information about Convert
Finish |  | 2018-03-19 | 2018-03-17 | Salma Ibrahem && Donia | Desgin interface
Finish |  | 2018-03-24 | 2018-03-19 | Donia && Mariam | Implementation
Finish |  | 2018-03-28 | 2018-03-24 | Salma Ibrahem | Test
Finish | Awatef ahmed | 2018-04-19 | 2018-04-08 | All Team | Menu | NUM 3
Finish |  | 2018-04-09 | 2018-04-08 | Sara | Gathering information about Menu
Finish |  | 2018-04-10 | 2018-04-09 | Salma Ahmed | Design interface about Menu
Finish |  | 2018-04-11 | 2018-04-10 | Donia | Design interface about Cost
Finish |  | 2018-04-13 | 2018-04-11 | Awatef | Implementation about List of Drinks
Finish |  | 2018-04-15 | 2018-04-13 | Salma Ibrahem && Mariam | Implementation about List of Food
Finish |  | 2018-04-18 | 2018-04-15 | Awatef && Salma Ibrahem && Mariam | Implementation about Costs
Finish |  | 2018-04-19 | 2018-04-18 | Salma Ahmed && Donia | Test
Not Started | Salma Ibrahem | 2018-04-29 | 2018-04-20 | All Team | Measuring Buttons | NUM 4
Not Started |  | 2018-04-21 | 2018-04-20 | Mariam | Sketching interface for buttons
Not Started |  | 2018-04-22 | 2018-04-21 | Donia | Design interface for buttons
Not Started |  | 2018-04-24 | 2018-04-22 | Sara | Implementation for Total and Reset buttons
Not Started |  | 2018-04-26 | 2018-04-24 | Salma Ahmed | Implementation for Receipt and Exit buttons
Not Started |  | 2018-04-27 | 2018-04-26 | Awatef | Testing
Not Started |  | 2018-04-29 | 2018-04-27 | Salma Ibrahem | Maintenance ana Upgrades