## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10 | Day 11 | Day 12 | Day 13 | Day 14
User Story #2 | 8 |  | Finish
gathering information about convert |  | salam | Finish | 8 | 4 | 3 | 5 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Background design |  | donia | Finish | 11 | 1 | 1 | 2 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
desgin interface |  | salam w donia | Finish | 14 | 2 | 0 | 3 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
implementation |  | donia w mariam | Finish | 20 | 0 | 0 | 0 | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
test |  | salam | Finish | 17 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #3 | 8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
gathering information about menu |  | sara | Finish | 18 | 4 | 3 | 3 | 2 | 1 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0
design interface about menu |  | salma ahmed | Finish | 19 | 0 | 0 | 0 | 3 | 2 | 3 | 0 | 4 | 1 | 0 | 2 | 2 | 1 | 1
design interface about cost |  | donia | Finish | 9 | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
implementation about list of drinks |  | awatef | Finish | 14 | 2 | 0 | 1 | 4 | 0 | 0 | 2 | 3 | 0 | 0 | 1 | 0 | 0 | 1
implementation about list of food |  | salma ibrahim&mariam | Finish | 14 | 2 | 0 | 3 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0
implementation about costs |  | mariam&awatef&salma ibrahim | Finish | 12 | 0 | 1 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 3
test |  | salma ahmed&&donia | Finish | 20 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 1 | 2 | 0 | 1 | 2 | 3 | 5
User story | 8
Sketching interface for buttons |  | Mariam | Finish | 9 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0
Design interface for buttons |  | Donia | Finish | 11 | 3 | 4 | 1 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Implementation for Total and Reset buttons |  | Sara | Finish | 17 | 0 | 4 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 3 | 2 | 1 | 1 | 1
Implementation for Receipt and Exit buttons |  | Salma Ahmed | Finish | 20 | 2 | 2 | 5 | 4 | 3 | 2 | 1 | 4 | 0 | 0 | 1 | 0 | 2 | 2
Testing |  | Awatef | Finish | 30 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2
Maintenance and Upgrades |  | Salma Ibrahem | Finish | 35 | 2 | 0 | 0 | 0 | 2 | 3 | 0 | 4 | 5 | 0 | 1 | 1 | 0 | 3
Total |  |  |  | 298 | 16 | 11 | 19 | 20 | 18 | 14 | 17 | 10 | 5 | 4 | 6 | 5 | 5 | 10
Ideal |  |  |  | 298 | 276.7143 | 255.4286 | 234.1429 | 212.8571 | 191.5714 | 170.2857 | 149 | 127.7143 | 106.4286 | 85.1429 | 63.8571 | 42.5714 | 21.2857 | 0
Actual |  |  |  | 298 | 280 | 266 | 250 | 227 | 220 | 200 | 160 | 120 | 100 | 70 | 55 | 40 | 25 | 0