## Sheet1
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10 | Day 11 | Day 12 | Day 13 | Day 14
User Story #4 | 8
Sketching interface for buttons |  | Mariam | Finish | 9 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0
Design interface for buttons |  | Donia | Finish | 11 | 3 | 4 | 1 | 1 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Implementation for Total and Reset buttons |  | Sara | Finish | 17 | 0 | 4 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 3 | 2 | 1 | 1 | 1
Implementation for Receipt and Exit buttons |  | Salma Ahmed | Finish | 20 | 2 | 2 | 5 | 4 | 3 | 2 | 1 | 4 | 0 | 0 | 1 | 0 | 2 | 2
Testing |  | Awatef | Finish | 30 | 1 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2
Maintenance ana Upgrades |  | Salma Ibrahem | Finish | 35 | 2 | 0 | 0 | 0 | 2 | 3 | 0 | 4 | 5 | 0 | 1 | 1 | 0 | 3
Total |  |  |  | 113 | 8 | 11 | 10 | 9 | 10 | 11 | 3 | 13 | 7 | 5 | 6 | 4 | 5 | 8
Ideal burndown |  |  |  | 122 | 113.2857 | 104.5714 | 95.8571 | 87.1429 | 78.4286 | 69.7143 | 61 | 52.2857 | 43.5714 | 34.8571 | 26.1429 | 17.4286 | 8.7143 | 0
Actual burndown |  |  |  | 122 | 110 | 111 | 105 | 91 | 81 | 72 | 68 | 60 | 49 | 35 | 33 | 20 | 7 | 0